## Sheet Assignments
ME 301 Final Project
Section 01
Fall 2010
Progress:
Name: | Description: |  | Sheet: | Started Modeling: | Finished Modeling: | Moved to Assembly Folder: | Part #s Assigned: | Email:
Matt | Crankcase Cover |  | 27 | 2010-11-04 | 2010-11-04 | 2010-11-09 | 2010-11-09 | John1234@vandals.uidaho.edu
| Flywheel/Driveshaft |  | 10 | 2010-11-04 | 2010-11-11 | 2010-11-11 | 2010-11-11
| Camshaft |  | 14 | 2010-11-12 | 2010-11-16 | 2010-11-17 | 2010-11-17
| Crankshaft |  | 1 | 2010-11-11 | 2010-11-16 | 2010-11-18 | 2010-11-18
Gustavo | Gear Guard |  | 17 |  |  |  |  | crazyt1234@q.com
| Crankcase Covers |  | 5 | 2010-11-09 | 2010-11-11 | 2010-11-11 | 2010-11-11 | guil1234@vandals.uidaho.edu
| Coolant Manifold |  | 4 | 2010-11-09 | 2010-11-09 | 2010-11-09 | 2010-11-09
| Intake Manifold |  | 12 | 2010-11-09
| Water Tube |  | 29 | 2010-11-05 | 2010-11-05 | 2010-11-09 | 2010-11-09
Jesus | Valve Assembly |  | 16 | 2010-11-11 | 2010-11-13 | 2010-11-17 | 2010-11-17 | jesus1234@hotmail.com
| Fuel Mixer Elbow/Oil Pan |  | 13 | 2010-11-05 | 2010-11-16 | 2010-11-16 | 2010-11-16
| Misc. Small Parts |  | 11 | 2010-11-03 | 2010-11-16 | 2010-11-16 | 2010-11-16
Josh | Crankcase |  | 2,3,18-21 | 2010-11-03 | 2010-12-03 | 2010-12-07 | 2010-12-07 | foss1234@vandals.uidaho.edu
Hieu | Crankcase |  | 2,3,18-21 | 2010-11-03 | 2010-12-03 | 2010-12-07 | 2010-12-07 | truo1234@vandals.uidaho.edu
Vince | Water Pump - Front,Back |  | 30,31 | 2010-11-05 |  |  |  | mayer1234@vandals.uidaho.edu
| Water Pump |  | 6 | 2010-11-05 | 2010-11-09 | 2010-11-11 | 2010-11-11
| Connecting Rod |  | 22 | 2010-11-07 | 2010-11-12 | 2010-11-15 | 2010-11-15
| Oil Line fitting |  | 24 | 2010-11-09 | 2010-11-16 | 2010-12-02 | 2010-12-02
Jacob | Cam Follower |  | 8 | 2010-11-11 | 2010-11-14 |  |  | jderig1234@vandals.uidaho.edu
| Oil Fill Pipe & Piston |  | 23 | 2010-11-05 | 2010-11-08 | 2010-11-11 | 2010-11-11
| Cylinder Water Jacket |  | 28 | 2010-11-09 | 2010-11-11 | 2010-11-11 | 2010-11-11
Nicholai | Bearing Caps |  | 26 | 2010-11-07 | 2010-11-11 | 2010-11-11 | 2010-11-11 | olso1234@vandals.uidaho.edu
| Compression Release |  | 25 | 2010-11-09 | 2010-11-11 | 2010-11-11 | 2010-11-11
| As Noted (various parts) |  | 7 | 2010-11-11 | 2010-11-18 | 2010-12-02 | 2010-12-02
| Fuel & Oil Pump |  | 15 | 2010-11-09 | 2010-11-11 | 2010-11-11 | 2010-11-11
| Cylinder |  | 9 | 2010-11-03 | 2010-11-09 | 2010-11-09 | 2010-11-09
Note on N9: Perry, Joel (jperry@uidaho.edu):
The Wright Stuff

## Part Information
ME 301 Final Project
Section 01
Fall 2010
Assembly #: | Part #: | Description: |  | Sub Assembly Assignment: | Assembled: | Drawing Assignment: | Drawing Completed: | Checked By: | Checked:
1 | 0 | Crankcase Assembly |  | Josh & Hieu | 2010-12-02 | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 1 | Crankcase |  | Josh & Hieu |  | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 2 | Crankcase Cover |  | Josh & Hieu |  | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 3 | Crankcase Cover (341022 Natl. Seal) |  | Josh & Hieu |  | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 4 | Crankcase Front Cover |  | Josh & Hieu |  | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 5 | Crankcase Cover Support Bar |  | Josh & Hieu |  | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 6 | Crankshaft |  | Josh & Hieu |  | Matt | 2010-12-07 | Nicholai | 2010-12-09
1 | 7 | Main Journal |  | Josh & Hieu |  | Hieu | 2010-12-07 | Matt | 2010-12-09
1 | 8 | Rod Journal |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 9 | Oil Pan 1 |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 10 | Oil Pan 2 |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 11 | Oil Fill Pipe |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 12 | Main Bearing Cap |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 13 | Gear Guard |  | Josh & Hieu |  | Gustavo | 2010-12-07 | Matt | 2010-12-09
1 | 14 | Gear Guard Mounting Clamp |  | Josh & Hieu |  | Gustavo | 2010-12-07 | Matt | 2010-12-09
1 | 15 | Flywheel |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 16 | Camshaft Center Bearing Cap |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 17 | Camshaft End Bearing Cap |  | Josh & Hieu |  | Hieu | 2010-12-08 | Matt | 2010-12-09
1 | 18 | Crankshaft Plug |  | Josh & Hieu |  | Matt | 2010-12-02 | Nicholai | 2010-12-09
1 | 19 | Crankshaft Gear |  | Josh & Hieu |  | Nicholai | 2010-12-02 | Matt | 2010-12-09
1 | 20 | Crankshaft Lock Nut |  | Josh & Hieu |  | Nicholai | 2010-12-02 | Matt | 2010-12-09
1 | 21 | Oil Line |  | Josh & Hieu |  | Nicholai | 2010-12-07 | Matt | 2010-12-09
2 | 0 | Cylinder & Piston Assembly |  | Jacob | 2010-12-02 | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 1 | Cylinder |  | Jacob |  | Nicholai | 2010-12-05 | Jesus | 2010-12-08
2 | 2 | Cylinder Water Jacket |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 3 | Cylinder Steel Shrink Ring |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 4 | Piston |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 5 | Connecting Rod |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 6 | Connecting Rod Cap |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 7 | Connecting Rod Washer |  | Jacob |  | Nicholai | 2010-12-07 | Jesus | 2010-12-08
2 | 8 | Valve |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 9 | Valve Guide |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 10 | Spring Cup |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 11 | Retainer Washer |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 12 | Retainer Nut |  | Jacob |  | Jacob | 2010-12-08 | Jesus | 2010-12-08
2 | 13 | Cylinder Bolt, Grade 5 |  | Jacob |  | Nicholai | 2010-12-07 | Jesus | 2010-12-08
2 | 14 | Cylinder Nut, Class 5 Thrd |  | Jacob |  | Nicholai | 2010-12-07 | Jesus | 2010-12-08
2 | 15 | Washer CRS |  | Jacob |  | Nicholai | 2010-12-07 | Jesus | 2010-12-08
3 | 0 | Camshaft Assembly |  | Matt | 2010-12-02 | Matt | 2010-12-02 | Jesus | 2010-12-07
3 | 1 | Camshaft |  | Matt |  | Matt | 2010-12-02 | Jesus | 2010-12-07
3 | 2 | Cam |  | Matt |  | Matt | 2010-12-02 | Jesus | 2010-12-07
3 | 3 | Canshaft Plug |  | Matt |  | Matt | 2010-12-02 | Jesus | 2010-12-07
3 | 4 | Hub |  | Matt |  | Matt | 2010-12-02 | Jesus | 2010-12-07
3 | 5 | Nut |  | Matt |  | Matt | 2010-12-02 | Jesus | 2010-12-07
3 | 6 | Camshaft Gear |  | Matt |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
3 | 7 | Cam Gear Lock Nut |  | Matt |  | Matt | 2010-12-02 | Jesus | 2010-12-07
4 | 0 | Rocker Arm Assembly |  | Jesus | 2010-12-02 | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 1 | Rocker Tower |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 2 | Rocker Shaft |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 3 | Rocker Arm Right |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 4 | Rocker Arm Left |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 5 | Rocker Arm Pin |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 6 | Roller |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 7 | Roller Pin |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 8 | Valve Push Rod |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 9 | Valve Push Rod (Head Piece) |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 10 | Valve Push Rod (Middle Slide Piece) |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
4 | 11 | Valve Push Rod (End Piece) |  | Jesus |  | Jesus | 2010-12-02 | Matt | 2010-12-08
5 | 0 | Coolant Manifold Assembly |  | Gustavo | 2010-11-30 | Gustavo | 2010-12-03 | Vince | 2010-12-07
5 | 1 | Coolant Manifold |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-07
5 | 2 | Main Water Tube |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-07
5 | 3 | Water Tube Fitting |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-07
5 | 4 | Water Tube Sleeve |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-07
6 | 0 | Intake Manifold Assembly |  | Gustavo | 2010-12-02 | Gustavo | 2010-12-03 | Vince | 2010-12-08
6 | 1 | Intake Manifold |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-08
6 | 2 | Fuel Mixer Elbow |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-08
6 | 3 | Manifold Extension (Elbow Ext.) |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-08
6 | 4 | Manifold Extension (Ends) |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-08
6 | 5 | Manifold Extension (Mids) |  | Gustavo |  | Gustavo | 2010-12-03 | Vince | 2010-12-08
7 | 0 | Compression Release Assembly |  | Nicholai | 2010-11-30 | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 1 | Rod |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 2 | Lever |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 3 | Pawl Stop |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 4 | End Stop |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 5 | Dome End Stop |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 6 | Interposer 1 |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 7 | Interposer 2 |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 8 | Rod Guide |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 9 | Interposer Pins |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 10 | Springs |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
7 | 11 | Cotter Pin |  | Nicholai |  | Nicholai | 2010-12-02 | Jesus | 2010-12-07
8 | 0 | Fuel and Oil Pumps Assembly |  | Nicholai | 2010-11-30 | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 1 | Body |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 2 | Cover Plate |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 3 | Primary Drive Shaft |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 4 | Secondary Drive Shaft |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 5 | Drive and Driven Gears |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 6 | U-Joint |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 7 | Assembly Bearing |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 8 | SL-BHMS 0.164-32x0.4375x0.4375-N |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 9 | SL-BHMS 0.164-32x0.75x0.75-N |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
8 | 10 | Helical Gear |  | Nicholai |  | Nicholai | 2010-12-02 | Vince | 2010-12-07
9 | 0 | Water Pump Assembly |  | Vince | 2010-11-30 | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 1 | Body - Front |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 2 | Body - Rear |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 3 | Impeller Body |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 4 | Impeller Shaft |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 5 | Main Bearing |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 6 | Packing Nut |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 7 | Drive Coupling (Brass, Steel Pin) |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 8 | Standoff |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
9 | 9 | Block Chain |  | Vince |  | Vince | 2010-12-02 | Nicholai | 2010-12-07
10 | 0 | Cam Follower Assembly |  | Jacob | 2010-12-02 | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 1 | Mount |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 2 | Arm |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 3 | Guide |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 4 | Roller |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 5 | Hinge Shaft |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 6 | Mount Block |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
10 | 7 | Roller Axle |  | Jacob |  | Vince | 2010-12-07 | Matt | 2010-12-07
The Wright Stuff